## Slide 1: FY 2015 Village of Pinehurst Strategic Plan Status Update As of September 30, 2014

## Slide 2
Village Council 3
Strategic objectives by perspective 4
Overview of the status of FY 2015 initiatives 5
Initiative status update:
Customer perspective 6
Internal perspective 8
Employee perspective 11
Financial perspective 12
Initiatives carried forward from FY 2014 13
FY 2015 Strategic Plan Status Update
Table of Contents

## Slide 3
FY 2015 Strategic Plan Status Update
Village Council
Nancy Fiorillo,
Mayor
Clark Campbell,
Councilmember
Claire Phillips,
Councilmember
John Cashion,
Mayor ProTem
John Strickland,
Treasurer

## Slide 4
FY 2015 Strategic Plan Status Update
Strategic Objectives by Perspective

## Slide 5
FY 2015 Strategic Plan Status Update
Overview of the Status of Strategic Initiatives at September 30, 2014
Council has added four initiatives since adoption of the FY 2015 SOP:
  HWY 211 Corridor Study
  Midland Rd Corridor Study
  HWY 5/Barrett Road Intersection Study
  Evaluate alternatives to make the Harness Track financially sustainable
Seven initiatives that were in progress at 6/30/14 have been carried forward to FY 2015 SOP
Staff recommends the Council consider the following changes for FY 2015 initiatives:
  Eliminating seven (7) initiatives
  Renaming four (4) initiatives
All other initiatives are in progress or will begin in a future quarter

## Slide 6
FY 2015 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Safeguard the Community | Achieve national accreditation in the Fire Department | -- | 
 | Partner with others to offer public safety education programs |  | 
 | Implement Command Central module to analyze crime data |  | 
 | Proactively investigate drug and related property crimes activities |  | 
Preserve the Character & Ambience of the Village | Develop a rating system for the appearance of public areas in partnership with CAC |  | Staff recommends changing the name of this initiative to "Develop a rating system for the appearance of public areas in partnership with the Beautification Committee"
 | Evaluate the consolidation of S&G and B&G (BIRDIE) | -- | 
 | Evaluate the code enforcement process (BIRDIE) |  | 
Promote Economic Opportunity | Incrementally expand Village Center into Village Place/Rattlesnake Corridor |  | 
 | Evaluate and enhance marketing efforts |  | Staff recommends eliminating this initiative
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 7
FY 2015 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Provide & Promote Safe Traffic & Pedestrian Mobility | Improve adequacy of street lighting in neighborhoods |  | 
 | Continue to work with NCDOT to identify a viable long-term solution for the traffic circle |  | 
 | Develop and implement a public education campaign for roadway safety |  | 
 | Collaborate with other jurisdictions to develop a HWY 211 corridor plan |  | Added per Council 7/23 meeting
 | Extend sidewalk and walkway system |  | 
 | Implement a GPS based software solution to track and analyze data on infrastructure maintenance and route management |  | 
 | Conduct the HWY5/Barrett Road Intersection Study |  | Added based on Council direction in Q2
 | Conduct the Midland Road Corridor Study |  | Added based on Council direction in Q2
Protect the Environment | Evaluate alternatives to reduce energy consumption for street lighting |  | 
 | Implement single-day collection system with automated yard debris |  | 
 | Increase public education on the benefits of recycling to encourage greater participation |  | 
Provide a Variety of Recreational and Cultural Opportunities | Expand cultural arts events in Village parks |  | 
 | Develop park facilities |  | 
 | Support the Given Memorial Library Expansion |  | 
 | Evaluate the need for indoor recreation facilities (BIRDIE) |  | 
Status at the end of the Quarter | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 8
FY 2015 Strategic Plan Status Update
Internal Perspective – Strategic Initiatives and Status
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Enhance Customer Service | Develop and implement a corporate communications strategy for keeping the public informed, considering a more frequent newsletter publication and eblasts post-Council meetings |  | 
 | Develop post event service survey for Fair Barn |  | 
 | Stream and post video and/or recordings of Council meetings on the Village website |  | Staff recommends changing the name of this initiative to “Post video and/or recordings of Council meetings on the Village website”
 | Redesign Village website to add more functionality and integrate it with a mobile app | -- | 
 | Conduct post-service surveys for building and development services |  | Staff recommends removing this initiative

## Slide 9
FY 2015 Strategic Plan Status Update
Internal Perspective – Strategic Initiatives and Status
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Continuously Improve Processes | Develop a contract management system |  | 
 | Automate employee P-Card Data Entry |  | Staff recommends removing this initiative
 | Automate A/P P-Card Data Entry |  | Staff recommends removing this initiative
 | Create a comprehensive orientation process for newly elected officials | -- | 
 | Conduct post-service surveys of building inspection customers |  | Staff recommends removing this initiative
 | Streamline inspection applications and processes to better coordinate with other departments | -- | 
 | Evaluate an integrated document management/imaging program (BIRDIE) | -- | 
 | Implement an E-Crash traffic accident solution |  | 
 | Streamline P&Z permits and applications (BIRDIE) |  | Staff recommends postponing this initiative to FY 2016
 | Evaluate opportunities for electronic submittal of P&Z forms and plans | -- | 

## Slide 10
FY 2015 Strategic Plan Status Update
Internal Perspective – Strategic Initiatives and Status
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Develop Collaborative Solutions | Partner with organizations to host cultural events at the Fair Barn |  | 
 | Evaluate alternative methods to obtain public input on Council related decisions (i.e. task forces, POA meetings, Peak Democracy, web module, etc.) |  | Staff suggests changing this initiative to "Implement online engagement tools to seek citizen input on Council related decisions"
 | Identify key partners and assign a Council liaison to each partner |  | 
Meet Legal & Regulatory Requirements | Complete Payment Card Industry (PCI) Compliance Project | -- | 
 | Increase capability to secure and monitor the Village network for legal compliance |  | 

## Slide 11
FY 2015 Strategic Plan Status Update
Employee Perspective – Strategic Initiatives and Status
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Optimize Volunteer Engagement | Develop an annual training program for volunteer committees |  | 
 | Develop a comprehensive volunteer reward and recognition program | -- | 
 | Develop a policy on volunteer and committee appointments |  | 
Recruit & Retain a Skilled & Diverse Workforce | Develop and implement a reward and recognition program |  | Staff recommends changing the name of this initiative to "Implement a reward and recognition program"
 | Develop a succession plan |  | 
 | Offer in-house training through the TOPS program and conduct the annual Employee Academy |  | 
 | Implement selected recommendations from the Compensation Study |  | 

## Slide 12
FY 2015 Strategic Plan Status Update
Financial Perspective – Strategic Initiatives and Status
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | Strategic Initiatives | Status | Recommended Changes to Original SOP Initiatives
Provide Value for Tax Dollars | Oversee the annexation of Cotswold |  | 
Maintain a Strong Financial Condition | Develop an annual budget that meets or exceeds established financial targets | -- | 
 | Maximize use of the Fair Barn |  | 
 | Evaluate alternatives to make the Harness Track financially sustainable | -- | Modified per Council 7/23 meeting from “Enhance marketing of the HT”
Invest in Capital | Light athletic field at Wicker Park |  | This initiative should be eliminated because it was not funded in FY 2015
 | Maintain VOP buildings and facilities |  | 
 | Effectively maintain current capital assets |  | 
 | Evaluate the sale of Village-owned land |  | 
 | Continue to enhance the Village roadways with the Annual Street Resurfacing Program |  | 

## Slide 13
FY 2015 Strategic Plan Status Update
Initiatives Carried Forward from FY 2014
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter
Strategic Objective | FY 2014 Strategic Initiatives Carried Forward | Status
Provide & Promote Safe Traffic & Pedestrian Mobility | Develop an alternative transportation master plan to identify locations of greenways, sidewalks, and bike paths | 
 | Conduct a Village-wide evaluation of street lighting needs | 
 | Install Opticom traffic device to improve response time and ensure safety of emergency personnel | 
Continuously Improve Processes | Centralize data access and promote business process analysis by maintatining, supporting, and utilizing SharePoint more effectively | 
 | Automate the TRC process | 
Recruit & Retain a Skilled & Diverse Workforce | Perform a formal compensation study to review current practices, pay scales, & position descriptions | 
 | Develop a Village wide employee recognition program |