## Slide 1: FY 2015 Village of Pinehurst Strategic Plan Q2 Status Update As of December 31, 2014
Notes: When Council adopted the FY 2015 SOP, you asked that staff provide quarterly updates on the status of implementation. This presentation represents the update at the end of the 2nd Quarter, or December 31, 2014.

## Slide 2
Village Council 3
Strategic objectives by perspective 4
Overview of the status of FY 2015 initiatives 5
Initiative status update:
Customer perspective 6
Internal perspective 8
Employee perspective 9
Financial perspective 10
Initiatives carried forward from FY 2014 11
Summary of the FY 2015 Q2 SOP Status Update 12
FY 2015 Strategic Plan Status Update
Table of Contents
Notes: We will review initiatives by BSC perspective and provide a summary of the recommended changes.

## Slide 3
FY 2015 Strategic Plan Status Update
Village Council
Nancy Fiorillo,
Mayor
Clark Campbell,
Councilmember
Claire Phillips,
Councilmember
John Cashion,
Mayor ProTem
John Strickland,
Treasurer
Notes: I would like to thank the Council for your leadership in strategic planning and providing the vision for our community, which staff strives to achieve through implementation of the SOP.

## Slide 4
FY 2015 Strategic Plan Status Update
Strategic Objectives by Perspective
Notes: Initiatives are grouped by the 15 strategic objectives in 4 BSC perspective areas: customer, internal, employee, and financial

## Slide 5
FY 2015 Strategic Plan Status Update
Overview of the Status of Strategic Initiatives at December 31, 2014
After adopting the FY 2015 SOP, Council made the following changes in Q1:
  Added four (4) initiatives
  Eliminated seven (7) initiatives
  Renamed four (4) initiatives
  Carried over seven (7) initiatives from FY 2014
In Q2, Council added the following initiative: Evaluate opportunities to renovate and enhance the current Public Services site
For Q2, staff recommends the following changes to the SOP:
  Rename one (1) initiative
  Eliminate/postpone five (5) initiatives:
    Evaluate the consolidation of S&G and B&G (BIRDIE)
    Streamline inspection applications and processes to better coordinate with other departments
    Automate the TRC process
    Evaluate an integrated document management/imaging program (BIRDIE)
    Develop a succession plan

## Slide 6
FY 2015 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Safeguard the Community | Achieve national accreditation in the Fire Department | -- | -- | 
 | Partner with others to offer public safety education programs |  |  | 
 | Implement Command Central module to analyze crime data |  |  | 
 | Proactively investigate drug and related property crimes activities |  |  | Staff recommends modifying the description to “Evaluate alternatives to proactively investigate drug and related property crimes activities.”
Preserve the Character & Ambience of the Village | Develop a rating system for the appearance of public areas in partnership with the Beautification Committee |  |  | 
 | Evaluate the consolidation of S&G and B&G (BIRDIE) | -- |  | Due to staff capacity and additional strategic initiatives added for FY 2015, staff recommends postponing this initiative to FY 2016
 | Evaluate the code enforcement process (BIRDIE) | -- |  | 
Promote Economic Opportunity | Incrementally expand Village Center into Village Place/Rattlesnake Corridor |  |  | 
 | Evaluate opportunities to renovate and enhance the current Public Services site |  |  | Added per Council direction in Q2
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 7
FY 2015 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Provide & Promote Safe Traffic & Pedestrian Mobility | Improve adequacy of street lighting in neighborhoods |  |  | 
 | Continue to work with NCDOT to identify a viable long-term solution for the traffic circle |  |  | 
 | Develop and implement a public education campaign for roadway safety |  |  | 
 | Collaborate with other jurisdictions to develop a HWY 211 corridor plan |  |  | 
 | Extend sidewalk and walkway system | -- | -- | 
 | Implement a GPS based software solution to track and analyze data on infrastructure maintenance and route management |  |  | 
 | Conduct the HWY5/Barrett Road Intersection Study |  |  | 
 | Conduct the Midland Road Corridor Study |  |  | 
Protect the Environment | Evaluate alternatives to reduce energy consumption for street lighting |  |  | 
 | Implement single-day collection system with automated yard debris |  |  | 
 | Increase public education on the benefits of recycling to encourage greater participation |  |  | 
Provide a Variety of Recreational and Cultural Opportunities | Expand cultural arts events in Village parks |  |  | 
 | Develop park facilities |  |  | 
 | Support the Given Memorial Library Expansion |  |  | 
 | Evaluate the need for indoor recreation facilities (BIRDIE) |  |  | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 8
FY 2015 Strategic Plan Status Update
Internal Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Enhance Customer Service | Develop and implement a corporate communications strategy for keeping the public informed, considering a more frequent newsletter publication and eblasts post-Council meetings |  |  | 
 | Develop post event service survey for Fair Barn |  |  | 
 | Post video and/or recordings of Council meetings on the Village website |  |  | 
 | Redesign Village website to add more functionality and integrate it with a mobile app | -- | -- | 
Continuously Improve Processes | Develop a contract management system |  |  | 
 | Create a comprehensive orientation process for newly elected officials | -- | -- | 
 | Streamline inspection applications and processes to better coordinate with other departments | -- |  | Staff recommends removing this initiative and replacing it with a broader departmental automation initiative in the future
 | Evaluate an integrated document management/imaging program (BIRDIE) | -- |  | Staff recommends postponing this initiative to FY 2016 due to changes in staffing and other higher priority initiatives
 | Implement an E-Crash traffic accident solution |  |  | 
 | Evaluate opportunities for electronic submittal of P&Z forms and plans | -- | -- | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 9
FY 2015 Strategic Plan Status Update
Internal and Employee Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Develop Collaborative Solutions | Partner with organizations to host cultural events at the Fair Barn |  |  | 
 | Implement online engagement tools to seek citizen input on Council related decisions |  |  | 
 | Identify key partners and assign a Council liaison to each partner |  |  | 
Meet Legal & Regulatory Requirements | Complete Payment Card Industry (PCI) Compliance Project | -- |  | 
 | Increase capability to secure and monitor the Village network for legal compliance |  |  | 
Optimize Volunteer Engagement | Develop an annual training program for volunteer committees |  |  | 
 | Develop a comprehensive volunteer reward and recognition program |  |  | 
 | Develop a policy on volunteer and committee appointments | -- |  | 
Recruit & Retain a Skilled & Diverse Workforce | Implement a reward and recognition program |  |  | 
 | Develop a succession plan |  |  | Staff recommends postponing this initiative to FY 2016 due to staff capacity
 | Offer in-house training through the TOPS program and conduct the annual Employee Academy |  |  | 
 | Implement selected recommendations from the Compensation Study |  |  | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 10
FY 2015 Strategic Plan Status Update
Financial Perspective – Strategic Initiatives and Status
Strategic Objective | Strategic Initiatives | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Provide Value for Tax Dollars | Oversee the annexation of Cotswold |  |  | 
Maintain a Strong Financial Condition | Develop an annual budget that meets or exceeds established financial targets | -- |  | 
 | Maximize use of the Fair Barn |  |  | 
 | Evaluate alternatives to make the Harness Track financially sustainable (BIRDIE) | -- | -- | 
Invest in Capital | Maintain VOP buildings and facilities |  |  | 
 | Effectively maintain current capital assets |  |  | 
 | Evaluate the sale of Village-owned land |  |  | 
 | Continue to enhance the Village roadways with the Annual Street Resurfacing Program |  |  | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 11
FY 2015 Strategic Plan Status Update
Initiatives Carried Forward from FY 2014
Strategic Objective | FY 2014 Strategic Initiatives Carried Forward | Q1 | Q2 | Recommended Changes to Original SOP Initiatives
Provide & Promote Safe Traffic & Pedestrian Mobility | Develop an alternative transportation master plan to identify locations of greenways, sidewalks, and bike paths |  |  | 
 | Conduct a Village-wide evaluation of street lighting needs |  |  | 
 | Install Opticom traffic device to improve response time and ensure safety of emergency personnel |  |  | 
Continuously Improve Processes | Centralize data access and promote business process analysis by maintaining, supporting, and utilizing SharePoint more effectively |  |  | 
 | Automate the TRC process |  |  | Staff recommends removing this initiative and replacing it with a broader departmental automation initiative in the future
Recruit & Retain a Skilled & Diverse Workforce | Perform a formal compensation study to review current practices, pay scales, & position descriptions |  |  | 
 | Develop a Village wide employee recognition program |  |  | 
 | Completed
 | In progress and on schedule
 | Staff recommends modifying or eliminating the initiative
-- | Initiative is scheduled to begin in a future quarter

## Slide 12
FY 2015 Strategic Plan Status Update
Summary of the FY 2015 Q2 SOP Status Update
Council added one (1) initiative in Q2
Four (4) initiatives were begun in Q2
Three (3) initiatives were completed in Q2
Staff recommends eliminating and/or postponing five (5) initiatives
Six (6) initiatives are scheduled to begin in Q3 or Q4:
  Achieve national accreditation in the Fire Department
  Extend sidewalk and walkway system
  Redesign Village website
  Create an orientation process for newly elected officials
  Evaluate opportunities for electronic submittal of P&Z forms
  Evaluate opportunities to make the HT financially feasible (BIRDIE)
Notes: Completed 3 initiatives:
  Policy on volunteer and committee appointments
  GPS software (mobile 311) in Public Services
  Given Memorial Library expansion ($300,000 payment)