## Slide 1: FY 2016 Village of Pinehurst Strategic Plan Status Update As of March 31, 2016

## Slide 2
Village Council 3
Strategic objectives by balanced scorecard perspective 4
Overview of the status of FY 2016 initiatives 5
Recommended modifications to the FY 2016 SOP 6
Initiative status update:
Customer perspective 7
Internal perspective 9
Employee perspective 10
Financial perspective 10
FY 2016 Strategic Plan Status Update
Table of Contents
2

## Slide 3
FY 2016 Strategic Plan Status Update
Village Council
Nancy Fiorillo,
Mayor
Clark Campbell,
Councilmember
Claire Berggren,
Councilmember
John Cashion,
Mayor ProTem
John Bouldry,
Treasurer
3

## Slide 4
FY 2016 Strategic Plan Status Update
Strategic Objectives by Balanced Scorecard Perspective
History, Charm, & Southern Hospitality
4

## Slide 5
FY 2016 Strategic Plan Status Update
Overview of the Status of FY 2016 Initiatives at March 31, 2016
There are a total of 37 Initiative Action Plans (IAPs) for FY 2016:
  10 were carried over from FY 2015
  27 were NEW IAPs for FY 2016
The following table indicates the status of IAPs at the end of March 31, 2016:
IAP Status | # of IAPs at 03/31/16
Completed | 14
In progress and on schedule | 16
In progress, but not on schedule | 3
Eliminated | 4
Total | 37
5

## Slide 6
FY 2016 Strategic Plan Status Update
Recommended Modifications to the FY 2016 SOP
Eliminate four IAPs:
  Implement recommendations from the evaluation of the sale of Village land
  Develop an “Adopt a Plant Bed” program
  Evaluate the effectiveness of the Village Council
  Install bike paths
Remove the “# of lf of bike lanes constructed” KPI from the FY 2016 Balanced Scorecard
Reinstate the IAP to “Evaluate the use of solar energy for Village facilities”
Carryforward three IAPs to FY 2017:
  Grounds maintenance BIRDIE
  Install greenways
  Redevelop the PS complex
6

## Slide 7
FY 2016 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Goal | Strategic Objective | Initiative Action Plan (IAP) | Q1 Status | Q2 Status | Q3 Status | Q3 Comments
Safeguard the Community | Deliver effective public safety services | Expand traffic pre-emption program to additional intersections in Village limits |  |  |  | 
 |  | Achieve national accreditation in the Fire Department |  |  |  | 
 |  | Evaluate alternative methods to proactively investigate and deter crime (BIRDIE) |  |  |  | 
Preserve the Character of Pinehurst & the Quality of Neighborhoods | Maintain a high level of overall appearance of Pinehurst public spaces | Evaluate the consolidation of Streets & Grounds and Buildings & Grounds (BIRDIE) |  |  |  | CARRYFORWARD: This IAP will likely extend until Q3 in FY 2017
 | Achieve a high level of compliance with Village codes and ordinances | Implement the recommendations of the Code Enforcement BIRDIE Team |  |  |  | 
 |  | Evaluate the code enforcement process (BIRDIE) (PY carryforward) |  |  |  | 
 | Maintain a high level of overall appearance of Pinehurst public spaces | Re-develop the Public Services campus |  |  |  | CARRYFORWARD: This IAP will likely extend until Q2 in FY 2017
 |  | Develop an "Adopt a Plant Bed" program with the Beautification Committee (ACE) |  |  |  | Recommend to DELETE, since Beautification Committee is not interested in taking on this program
Promote Economic Opportunity | Support economic and business development to meet the needs of Pinehurst residents and visitors | Support Pinehurst businesses through collaboration with Pinehurst Business Partners |  |  |  | 
 |  | Incrementally expand the Village Center into Village Place/Rattlesnake Corridor |  |  |  | 
Legend | 
 | IAP begins in a future quarter
 | IAP is in progress and on schedule
 | IAP is in progress, but not on schedule
 | IAP has been completed
 | Recommend eliminating the IAP
7

## Slide 8
FY 2016 Strategic Plan Status Update
Customer Perspective – Strategic Initiatives and Status
Goal | Strategic Objective | Initiative Action Plan (IAP) | Q1 Status | Q2 Status | Q3 Status | Q3 Comments
Provide & promote multi-modal transportation connectivity | Provide a safe and well-maintained network of streets, sidewalks, greenways, and bike paths | Conduct Midland Road corridor study (PY carryforward) |  |  |  | 
 | Provide a safe and well-maintained network of streets, sidewalks, greenways, and bike paths | Install sidewalks and/or greenways according to the Pedestrian Master Plan |  |  |  | CARRYFORWARD: Greenway will not be completed by 6/30/16 due to wetland issues encountered; Will extend into FY 2017
 | Provide a safe and well-maintained network of streets, sidewalks, greenways, and bike paths | Install bike paths according to the Bicycle Master Plan |  |  |  | Recommend to DELETE, per Council direction
 | Provide for efficient traffic flow with minimal congestion | Make intersection improvements at McKenzie Rd and Hwy 5 and Barrett Rd and Hwy 5 |  |  |  | 
Promote environmental sustainability | Conserve natural resources | Evaluate the use of solar energy for Village facilities |  |  |  | 
Promote an active, healthy community | Provide adequate recreational facilities | Develop a comprehensive recommendation for a new Community Center Facility |  |  |  | 
 | Provide adequate recreational facilities | Develop Rassie Wicker Park facilities |  |  |  | Behind schedule, but expect to complete by 6/30/16
 | Provide recreation programs and leisure activities for all ages | Establish a P&R internship program |  |  |  | 
Legend | 
 | IAP begins in a future quarter
 | IAP is in progress and on schedule
 | IAP is in progress, but not on schedule
 | IAP has been completed
 | Recommend eliminating the IAP
8

## Slide 9
FY 2016 Strategic Plan Status Update
Internal Perspective – Strategic Initiatives and Status
Goal | Strategic Objective | Initiative Action Plan (IAP) | Q1 Status | Q2 Status | Q3 Status | Q3 Comments
Professionally Manage a High Performing Organization | Effectively communicate with customers in a timely and consistent manner | Develop and implement a corporate communications strategy for keeping the public informed, considering a more frequent newsletter publication and eblasts post-Council meetings (PY carryforward) |  |  |  | 
 | Continually improve the effectiveness and efficiency of key processes | Develop a contract management system (PY carryforward) |  |  |  | 
 |  | Continue to utilize the Baldrige excellence framework to improve organizational performance |  |  |  | 
 |  | Develop an organization wide complaint management process -VOP 311 (BIRDIE) |  |  |  | 
 |  | Develop a mechanism to share best practices between departments and evaluate the effectiveness (ACE) |  |  |  | 
 |  | Review key Village processes annually for opportunities for improvement |  |  |  | 
 |  | Complete Payment Card Industry (PCI) Compliance (PY carryforward) |  |  |  | 
 |  | Develop a method to evaluate the effectiveness of the Village Council (ACE) |  |  |  | Recommend to DELETE, per Council direction
 |  | Develop a comprehensive orientation process for newly elected officials (PY carryforward) |  |  |  | 
Legend | 
 | IAP begins in a future quarter
 | IAP is in progress and on schedule
 | IAP is in progress, but not on schedule
 | IAP has been completed
 | Recommend eliminating the IAP
9

## Slide 10
FY 2016 Strategic Plan Status Update
Internal, Workforce, & Financial Perspectives - Strategic Initiatives and Status
Goal | Strategic Objective | Initiative Action Plan (IAP) | Q1 Status | Q2 Status | Q3 Status | Q3 Comments
Professionally Manage a High Performing Organization | Generate collaborative solutions | Identify key partners and assign a Council liaison to each partner (PY carryforward) |  |  |  | 
 | Leverage technology to enhance Village operations | Increase capability to secure and monitor the Village computer network for legal compliance |  |  |  | 
 |  | Redesign Village website to add more functionality and integrate it with a mobile app (PY carryforward) |  |  |  | 
Recruit and develop a skilled and diverse workforce | Recruit, train, engage, and reward volunteers | Develop a comprehensive volunteer reward and recognition program (PY carryforward) |  |  |  | 
 |  | Develop a policy on volunteer and committee appointments (PY carryforward) |  |  |  | 
 | Train, develop, and engage employees | Review and revise the in-house TOPS training program (ACE) |  |  |  | Behind schedule, but expect to complete by 6/30/16
 | Reward and recognize employees | Implement a reward and recognition program (ACE) |  |  |  | 
Maintain a strong financial condition | Meet or exceed Village established financial targets | Evaluate alternative revenue sources for the Village |  |  |  | 
 |  | Implement the recommendations from the evaluation of the sale of Village owned land |  |  |  | Recommend to DELETE and incorporate into Land Use Analysis planned for FY 2017
 |  | Implement BIRDIE Team recommendations to ensure the financial sustainability of the Harness Track |  |  |  | 
Legend | 
 | IAP begins in a future quarter
 | IAP is in progress and on schedule
 | IAP is in progress, but not on schedule
 | IAP has been completed
 | Recommend eliminating the IAP
10